# SCOPE ALIGNMENT DOCUMENT

## PepsiCo AppDynamics Licensing Consumption Dashboard - Full Implementation

Version: 2.0
Date: October 2025
Project Type: Comprehensive Solution
Estimated Effort: 320-380 hours – Internal Use Only
Estimated Timeline: 10-11 weeks – Internal Use Only

## 1. EXECUTIVE SUMMARY

### 1.1 Purpose

Deliver a comprehensive license management solution that establishes complete governance, cost visibility, and chargeback capabilities for PepsiCo's AppDynamics licensing, replacing manual spreadsheet tracking with a fully automated, enterprise-grade dashboard solution.

### 1.2 Business Objectives

- Primary Goal: Create an authoritative source of truth for AppDynamics license consumption, costs, and allocations

- Enable: Full cost transparency with department-level chargeback capabilities

- Provide: Advanced analytics including Peak vs. Pro attribution and architectural insights

- Establish: Future-proof architecture supporting tool migration and expansion

- Deliver: Enterprise-grade reliability with comprehensive data governance

### 1.3 Key Deliverables

- Automated data collection with full reconciliation capabilities

- PostgreSQL database with comprehensive schema

- Multi-panel Grafana dashboards with advanced analytics

- Per-application cost tracking with Peak vs. Pro differentiation

- Monolith vs. Microservices categorization and reporting

- Advanced forecasting with multiple scenarios

- Complete documentation suite including migration guides

- Full chargeback and showback capabilities

### 1.4 Success Metrics

- Enable department-level cost chargebacks

- Achieve ±2% accuracy with full attribution

- Dashboard response time <5 seconds

- 100% application ownership mapping

- Reduce manual effort by 95%

- Support strategic architectural decisions

## 2. COMPREHENSIVE PROJECT SCOPE

### 2.1 License Coverage & Analytics

Full Scope Includes:

- Detailed usage tracking by license type:

  - APM (Application Performance Management)

  - RUM (Real User Monitoring - MRUM/BRUM)

  - Synthetic Monitoring

  - Database Monitoring

- Peak vs. Pro Usage Differentiation:

  - Application-level attribution

  - Cost implications analysis

  - Optimization opportunity identification

  - Tier-based reporting and trends

- Monolith vs. Microservices Categorization:

  - Architectural pattern classification

  - Roll-up reporting by architecture type

  - License efficiency analysis by pattern

  - Transformation impact tracking

- Comprehensive Attribution:

  - Per-application license consumption

  - Node and server level tracking

  - Drill-down capabilities to component level

  - Complete audit trail

### 2.2 Cost Analysis & Financial Management

Full Scope Includes:

- Multi-Dimensional Cost Allocation:

  - By license type (APM, RUM, Synthetic, DB)

  - By license tier (Peak vs. Pro)

  - By application

  - By business sector

  - By owner/team

  - By H-code (cost center)*

  - By architecture type

*Note: H-code population in ServiceNow is PepsiCo's responsibility. System will utilize H-code when present and provide manual override capability when absent.

H-Code will be 10-20 digit number and will be a tag in AppDynamics

- Chargeback & Showback Capabilities:

  - Automated cost attribution to departments

  - Monthly billing report generation

  - Cost allocation rules engine

  - Shared service cost distribution

  - Exception handling workflows

- Financial Features:

  - Contract-based pricing with renewal periods

  - Dynamic rate configuration

  - Budget variance analysis

  - Cost optimization recommendations

  - What-if scenario modeling

### 2.3 Trend Analysis & Forecasting

Full Scope Includes:

- Advanced Historical Analysis:

  - Pattern identification and anomaly detection

  - Seasonal trend analysis

  - Growth rate calculations

  - Utilization efficiency metrics

- Sophisticated Forecasting:

  - Multiple algorithms (linear, exponential, seasonal)

  - Confidence intervals and statistical modeling

  - 12, 18, and 24-month projections

  - Scenario-based planning (best/likely/worst case)

  - Capacity planning recommendations

- Predictive Analytics:

  - License exhaustion predictions

  - Budget overrun alerts

  - Growth trajectory modeling

  - Optimization opportunity identification

### 2.4 Data Integration & Enrichment

#### 2.4.1 AppDynamics Integration

Comprehensive Data Collection:

- Application, tier, node, and server configuration

- License usage telemetry with Peak vs. Pro metadata

- Real-time and historical metrics

- Application tags and custom properties

- Architectural pattern indicators

Technical Implementation:

- OAuth2 secured integration

- Incremental and full-load capabilities

- Automated retry and error handling

- Rate limiting and throttling

- Data validation and quality checks

#### 2.4.2 ServiceNow Integration

Full CMDB & Request Integration:

- CMDB Tables:

  - cmdb_ci_service - Service configuration items

  - cmdb_ci_server - Server configuration items

  - cmdb_rel_ci - Relationship mappings

- Request Data:

  - Application approval workflows

  - Ownership chain and approvers

  - Change request history

  - Incident correlation data

Fields Retrieved:

- Application Service name

- Owner (primary and secondary)

- Business Sector

- H-code (cost center) - when populated*

- Approvers and stakeholders

- Organizational hierarchy

- Support group assignments

*PepsiCo Responsibility: Ensure H-code field is populated in ServiceNow for accurate cost allocation. System provides manual override table for unpopulated H-codes.

#### 2.4.3 Data Reconciliation Engine

Automated Matching & Governance:

- Cross-system name reconciliation

- Fuzzy matching algorithms

- Manual mapping UI for exceptions

- Data steward workflow integration

- Confidence scoring for matches

- Audit trail for all mappings

- Regular reconciliation reports

### 2.5 Architecture

#### 2.5.1 Enterprise Infrastructure

- Platform: Linux VM cluster with HA capability

- Database: PostgreSQL 16 with replication

- Visualization: Grafana Enterprise with SSO/RBAC

- ETL: Containerized Python with orchestration

- Scheduling: Enterprise scheduler (Airflow/similar)

- Security: Vault-based secrets management

#### 2.5.2 Modular Plugin Architecture

Future-Proof Design:

- Tool-agnostic core engine

- Abstraction layers for monitoring tools

- Plugin interfaces for easy tool addition/replacement

- Standardized data models

- Migration-ready architecture

- API-first design principles

#### 2.5.3 Comprehensive Database Schema

Fact Tables:

- license_usage_fact - Granular usage metrics

- license_cost_fact - Calculated costs with allocation

- forecast_fact - Prediction data

- chargeback_fact - Department charges

Dimension Tables:

- applications_dim - Application metadata

- owners_dim - Ownership hierarchy

- sectors_dim - Business sectors

- capabilities_dim - License types

- architecture_dim - Monolith/Microservices

- time_dim - Time hierarchy

Configuration Tables:

- price_config - Pricing rules and overrides

- allocation_rules - Cost distribution logic

- mapping_overrides - Manual reconciliation

- forecast_models - Algorithm configurations

Audit Tables:

- etl_execution_log - Job history

- data_lineage - Full audit trail

- reconciliation_log - Matching history

- user_actions - Administrative changes

### 2.6 Dashboard & Visualization

#### 2.6.1 Multi-Tab Grafana Dashboard Suite

Tab 1: Executive Overview

- Monthly summary with KPIs

- Budget vs. actual with variance

- Top consumers by department

- Cost trends and projections

- Critical alerts and recommendations

Tab 2: Usage by License Type

- Separate panels for APM, RUM, Synthetic, DB

- Current utilization vs. capacity

- Historical trends by type

- Peak vs. Pro breakdown

- Optimization opportunities

Tab 3: Cost Analytics

- Multi-dimensional cost breakdowns

- Chargeback summary by department

- Cost allocation waterfall

- Trending by sector/owner/H-code

- Budget variance analysis

Tab 4: Peak vs. Pro Analysis

- Application-level tier usage

- Cost impact analysis

- Downgrade opportunities

- Savings potential calculator

- Historical tier changes

Tab 5: Architecture Analysis

- Monolith vs. Microservices distribution

- License efficiency by architecture

- Transformation tracking

- Cost per architecture pattern

- Migration impact analysis

Tab 6: Trends & Forecasts

- 24-month historical view

- Multi-scenario forecasts

- Confidence bands

- Seasonal pattern analysis

- Capacity planning graphs

Tab 7: Allocation & Chargeback

- Department-level charges

- Drill-through to applications

- Shared service allocations

- Dispute tracking

- Invoice generation

Tab 8: Admin Panel

- Price configuration manager

- Mapping reconciliation UI

- ETL health monitoring

- Data quality dashboard

- User management

- Audit logs

#### 2.6.2 Advanced Interactive Features

- Dynamic multi-level filtering

- Cross-tab navigation

- Drill-through capabilities

- Custom date ranges

- Saved views and bookmarks

- Automated report scheduling

- Export to multiple formats

- API access for external tools

### 2.7 Configurability & Maintenance

Administrative Capabilities:

- Price Management:

  - Dynamic pricing configuration

  - Effective date management

  - Tier-based rate tables

  - Contract renewal handling

- Data Governance:

  - Manual mapping interface

  - Reconciliation workflows

  - Data quality thresholds

  - Exception approval process

- System Management:

  - ETL schedule configuration

  - Alert threshold management

  - User role administration

  - Backup configuration

### 2.8 Documentation & Knowledge Transfer

Comprehensive Documentation Suite:

- User Guide

  - Complete dashboard navigation

  - Feature descriptions and use cases

  - Report interpretation guide

  - Best practices

- Technical Architecture Documentation

  - System design and components

  - Data flow diagrams

  - Integration specifications

  - Security architecture

- Data Dictionary

  - Complete field definitions

  - Calculation methodologies

  - Business rules documentation

  - Metric definitions

- Configuration Guide

  - Pricing updates procedures

  - Mapping maintenance

  - Admin tasks and workflows

  - Troubleshooting guide

- Migration Guide

  - Tool replacement procedures

  - Data migration strategies

  - Rollback procedures

  - Testing protocols

- Extension Guidelines

  - Adding new data sources

  - Creating custom plugins

  - API development guide

  - Integration patterns

- Operations Runbook

  - Daily/weekly/monthly tasks

  - Health check procedures

  - Incident response

  - Disaster recovery

Knowledge Transfer Program:

- Technical deep-dive sessions (3)

- End-user training workshops (2)

- Admin training (2 sessions)

- Recorded video tutorials

- Q&A sessions

- 30-day post-deployment support

## 3. PREREQUISITES (PEPSICO RESPONSIBILITIES)

### 3.1 Infrastructure (Due: Project Kickoff)

- Linux VM(s) provisioned per specifications:

  - Primary: 16 vCPUs, 64GB RAM, 1TB disk

  - Secondary (optional HA): Same specifications

  - RHEL 8+ or Ubuntu 20.04+

  - Network access to all required systems

  - Load balancer configuration (if HA)

### 3.2 AppDynamics Access (Due: Week 1)

- OAuth2 client credentials with appropriate scopes

- Full read permissions for:

  - All license metrics

  - Application configurations

  - Node and tier metadata

  - Custom properties and tags

- API documentation and rate limits

- Test and production endpoints

### 3.3 ServiceNow Access (Due: Week 1)

- Integration account with read access to:

  - CMDB tables (cmdb_ci_service, cmdb_ci_server, cmdb_rel_ci)

  - Request tables (sc_request, sc_req_item)

  - User and group tables

- REST API endpoints and authentication

- Development instance for testing

### 3.4 Data Alignment (Critical - Due: Week 1)

H-Code Population (PepsiCo Responsibility):

- Critical Requirement: PepsiCo must ensure H-code (cost center) field is populated in ServiceNow CMDB  AppDynamics

- Minimum Coverage: 90% of active applications must have H-code populated

- Quality Standards: H-codes must be valid and current

- Update Process: Regular update process must be established

- Fallback Process: For missing H-codes, PepsiCo must provide:

  - Manual override table with application-to-H-code mappings

  - Designated owner for maintaining overrides

  - Monthly update commitment

Additional Data Requirements:

- Application tagging strategy for Peak/Pro identification

- Architectural classification (Monolith/Microservices) approach

- Join key validation between systems

- Current pricing and contract terms

- Budget targets and thresholds

### 3.5 Security & Access (Due: Week 2)

- SSO configuration and testing

- RBAC group definitions and mappings

- Firewall rules and network connectivity

- Certificate management (if required)

- Secrets management approval

### 3.6 Validation Data (Due: Week 2)

- 6-12 months historical reference data

- Current cost allocation spreadsheets

- Known exceptions and overrides

- Test scenarios for UAT

- Success criteria definitions

### 3.7 Organizational Readiness (Due: Week 3)

- Identified stakeholders for each department

- Chargeback process approval

- Dispute resolution process defined

- Communication plan approved

- Change management plan

## 4. PROJECT TIMELINE (INTERNAL USE ONLY)

### 10-11 Week Delivery Schedule

Weeks 1-2: Foundation & Design

- ✓ Complete requirements gathering

- ✓ Validate all prerequisites

- ✓ Finalize architecture design

- ✓ Confirm data mappings and H-codes

- ✓ Setup development environment

Weeks 3-4: Core Data Integration

- ✓ Build AppDynamics comprehensive ETL

- ✓ Implement Peak vs. Pro attribution logic

- ✓ Create ServiceNow full integration

- ✓ Develop reconciliation engine

- ✓ Design and implement database schema

Weeks 5-6: Advanced Analytics

- ✓ Build cost allocation engine

- ✓ Implement chargeback calculations

- ✓ Create forecasting models

- ✓ Develop architectural categorization

- ✓ Build optimization algorithms

Weeks 7-8: Dashboard Development

- ✓ Create all 8 dashboard tabs

- ✓ Implement drill-through navigation

- ✓ Build admin interfaces

- ✓ Configure RBAC and security

- ✓ Develop automated reports

Week 9: Integration Testing

- ✓ End-to-end system testing

- ✓ Performance optimization

- ✓ Security testing

- ✓ Data validation

- ✓ Bug fixes and refinements

Week 10: UAT & Training

- ✓ User acceptance testing

- ✓ Chargeback validation

- ✓ Training sessions

- ✓ Documentation review

- ✓ Final adjustments

Week 11: Deployment & Stabilization

- ✓ Production deployment

- ✓ Data migration

- ✓ Go-live support

- ✓ Knowledge transfer

- ✓ Project handover

## 5. ACCEPTANCE CRITERIA

### 5.1 Functional Requirements

All license types tracked with Peak vs. Pro differentiation
Monolith vs. Microservices categorization operational
Per-application costs calculated and validated
Chargeback reports generated for all departments with H-codes
All 8 dashboard tabs fully functional
Forecasting models producing projections with confidence intervals
Reconciliation engine matching >95% of applications
Manual mapping UI operational for exceptions

### 5.2 Data Quality

### Cost calculations verified for all attribution levels
H-code coverage >90% (PepsiCo responsibility)
Historical data loaded for 12+ months
Forecast accuracy validated against historical patterns

### 5.3 Technical Requirements

### ETL jobs completing within defined windows
SSO/RBAC fully configured and tested
Plugin architecture validated with test case
All security requirements met

### 5.4 Documentation & Training

All 7 documentation deliverables completed
Training sessions conducted and recorded
Knowledge transfer validated by questionnaire
Admin users certified on system operation

### 5.5 Stabilization

5 business days post-deployment monitoring
Zero Sev-1/Sev-2 issues open
Chargeback cycle successfully completed
Executive sponsor sign-off obtained

## 6. CONSTRAINTS & ASSUMPTIONS

### 6.1 Constraints

- Dependent on H-code availability in ServiceNow AppDynamics

- No modifications to source systems

- Must work within existing security policies

### 6.2 Assumptions

- Critical: PepsiCo will populate H-codes in ServiceNow AppDynamics (>90% coverage)

- All prerequisites met on schedule

- APIs remain stable during development

- Peak/Pro differentiation is achievable via AppDynamics metadata

- Architectural classification can be determined programmatically

- SMEs available for validation and UAT

### 6.3 Dependencies

- H-code population completed before Week 3

- ServiceNow CMDB data quality sufficient

- AppDynamics tagging strategy implemented

- Network connectivity approved

- Stakeholder availability for decisions

## 7. RISK MANAGEMENT

### 7.1 Critical Risks

| Risk | Impact | Probability | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| H-codes not populated | Chargeback impossible | High | PepsiCo must commit to population; manual override table as backup | PepsiCo |
| Peak/Pro metadata missing | Cannot differentiate tiers | Medium | Implement tagging strategy; use heuristics as fallback | Joint |
| Architecture classification complex | Delayed categorization | Medium | Start with manual classification; automate over time | Delivery Team |
| Reconciliation <95% match | Poor data quality | Low | Manual mapping UI; data steward process | Joint |
| Performance issues with full scope | User dissatisfaction | Low | Optimize queries; implement caching | Delivery Team |
| Stakeholder availability | Delayed decisions | Medium | Identify backups; escalation path | PepsiCo |

### 7.2 H-Code Specific Risk Management

Given the critical dependency on H-codes for chargeback:

- Week 1: Audit current H-code population percentage

- Week 2: If <90%, escalate to executive sponsor

- Week 3: Go/No-Go decision on chargeback functionality

- Fallback: Implement manual override table with monthly updates

- Long-term: PepsiCo to implement data quality program

## 8. PROJECT TEAM

### 8.1 PepsiCo Team

- Executive Sponsor: Strategic decisions, H-code population accountability

- Business Owner: Requirements, UAT, chargeback validation

- Data Governance Lead: H-code quality, CMDB accuracy

- Technical Lead: Architecture, integration approvals

- Department Representatives: Chargeback validation

- SMEs: Domain expertise, data validation

### 8.2 Delivery Team

- Project Manager: Overall delivery accountability

- Solution Architect: Architecture and design

### 8.3 RACI Matrix

| Activity | Sponsor | Business | Data Gov | Delivery |
| --- | --- | --- | --- | --- |
| H-code Population | A | R | R | I |
| Requirements | I | A | C | R |
| Architecture | I | I | C | R |
| Data Quality | A | C | R | C |
| Development | I | C | I | R |
| Chargeback Validation | A | R | C | C |
| UAT | I | A | C | R |
| Deployment | A | I | I | R |

R=Responsible, A=Accountable, C=Consulted, I=Informed

## 9. COMMUNICATION PLAN

### 9.1 Governance Structure

- Steering Committee: Bi-weekly (Executives)

- Project Team Meeting: Weekly (All team members)

- Technical Deep Dive: Weekly (Technical team)

- Data Quality Review: Weekly (Focus on H-codes)

### 9.2 Status Reporting

- Executive dashboard updated weekly

- Detailed status report every Friday

- Risk register reviewed weekly

- H-code population metrics tracked daily (Weeks 1-3)

## 10. BUDGET & COMMERCIAL (INTERNAL USE ONLY)

### 10.1 Project Costs

- Professional Services: 320-380 hours @ blended rate

  - Foundation & Design: 60-70 hours

  - Data Integration: 70-80 hours

  - Advanced Analytics: 50-60 hours

  - Dashboard Development: 60-70 hours

  - Testing & Validation: 40-50 hours

  - Training & Documentation: 40-50 hours

- Software Licenses:

  - Grafana Enterprise (if required)

  - PostgreSQL (open source)

- Infrastructure: Provided by PepsiCo

## 11. SUCCESS CRITERIA SUMMARY

The project will be deemed successful when:

- Full Attribution Achieved: Peak vs. Pro and Monolith vs. Microservices tracking operational

- Chargeback Enabled: Departments receiving accurate monthly charges (requires H-codes)

- Advanced Analytics Working: Forecasting, optimization, and recommendations functional

- Knowledge Transferred: Teams trained and documentation delivered

- Stabilization Complete: 5 days post-go-live without critical issues

## 12. APPENDICES (TBD)